## Sheet1
Sprint | user-stories | Task | Initial Estimate
Sprint 1 | As a user i want to view my tasks so i can see what tasks i have put up | Create the Task model class | 30 min
|  | Create the Task ViewModel | 30 min
|  | Implement data binding between ViewModel and UI | 30 min
|  | Design and structure the task viewing UI | 30 min
|  | Implement task retrieval from list | 30 min
|  | Display tasks in list view | 30 min
| As a user i want to add a new task so i can keep track of things i need to do | Design and structure the task creation UI | 30 min
|  | Implement the AddTask method in ViewModel | 30 min
|  | Implement input validation for task details | 30 min
|  | Store new tasks in list | 30 min
|  | Update UI after task addition | 30 min
| As a user i want to edit my tasks so i can update it's details | Design and structure the task editing UI | 30 min
|  | Implement the EditTask method in ViewModel | 30 min
|  | Implement input validation for task updates | 30 min
|  | Implement update logic in list | 30 min
|  | Reflect changes on the UI | 30 min
| As a user i want to delete my tasks so can remove a task i no longer want to complete | Design and structure the task deletion UI | 30 min
|  | Implement the DeleteTask method in ViewModel | 30 min
|  | Implement deletion confirmation prompt | 30 min
|  | Remove tasks from list | 30 min
|  | Update UI after task deletion | 30 min
| As a user i want to mark my tasks complete so i can track my progress | Design and structure the task completion UI | 30 min
|  | Implement the CompleteTask method in ViewModel | 30 min
|  | Implement task status update logic | 30 min
|  | Update list when a task is marked as complete | 30 min
|  | Reflect completed status on the UI | 30 min